## Milestones & Activities
Milestone | Activity | Expected Output | Start Date | End Date | Status
Environment & Foundations | Install Python, VS Code, Git, Ollama | Dev environment ready | 18 Jan 2026 | 18 Jan 2026 | Completed
Environment & Foundations | Run quantized 7B model in Ollama | LLM responds locally | 18 Jan 2026 | 18 Jan 2026 | Completed
Environment & Foundations | Python script calling Ollama | Prompt-response works | 19 Jan 2026 | 19 Jan 2026 | Completed
Environment & Foundations | Install sentence-transformers & test embeddings | Embedding vectors created | 20 Jan 2026 | 20 Jan 2026 | Completed
Environment & Foundations | Install FAISS & persist index | FAISS index stored | 21 Jan 2026 | 21 Jan 2026 | Completed
Environment & Foundations | Implement semantic retrieval | Relevant chunks retrieved | 22 Jan 2026 | 22 Jan 2026 | Completed
Environment & Foundations | Build basic RAG pipeline | Context-based answer | 23 Jan 2026 | 23 Jan 2026 | Completed
Environment & Foundations | Stabilization & cleanup | Stable baseline | 24 Jan 2026 | 24 Jan 2026 | Completed
Bare Act Legal RAG | Extract text from Bare Act PDFs | Bare Act text ready | 25 Jan 2026 | 25 Jan 2026 | Completed
Bare Act Legal RAG | Chunk text logically | Clean chunks | 26 Jan 2026 | 26 Jan 2026 | Completed
Bare Act Legal RAG | Detect sections & headings | Section metadata | 27 Jan 2026 | 27 Jan 2026 | Completed
Bare Act Legal RAG | Embed & index Bare Acts | Bare Acts searchable | 28 Jan 2026 | 28 Jan 2026 | Completed
Bare Act Legal RAG | Implement legal retrieval | Correct sections returned | 29 Jan 2026 | 29 Jan 2026 | Completed
Bare Act Legal RAG | Hallucination-safe prompts | No fake sections | 30 Jan 2026 | 30 Jan 2026 | Completed
Bare Act Legal RAG | End-to-end demo | Bare Act RAG works | 31 Jan 2026 | 31 Jan 2026 | Completed
UI & Fact Collection | Create Streamlit skeleton | UI launches | 01 Feb 2026 | 01 Feb 2026 | Completed
UI & Fact Collection | Plain-language fact input | Facts captured | 02 Feb 2026 | 02 Feb 2026 | Completed
UI & Fact Collection | Normalize facts into JSON | Structured facts | 03 Feb 2026 | 03 Feb 2026 | Completed
UI & Fact Collection | Validate missing facts | Validation works | 04 Feb 2026 | 04 Feb 2026 | Completed
UI & Fact Collection | UI + Bare Act RAG integration | Legal Q&A via UI | 05 Feb 2026 | 06 Feb 2026 | Completed
CrewAI Core Agents | Install & test CrewAI | CrewAI running | 07 Feb 2026 | 07 Feb 2026 | Completed
CrewAI Core Agents | Define agent roles | Roles documented | 08 Feb 2026 | 08 Feb 2026 | Completed
CrewAI Core Agents | Facts Collector Agent | Structured facts output | 09 Feb 2026 | 09 Feb 2026 | Completed
CrewAI Core Agents | Bare Act Research Agent | Sections retrieved | 10 Feb 2026 | 10 Feb 2026 | Completed
CrewAI Core Agents | Legal Opinion Agent | Plain legal opinion | 11 Feb 2026 | 12 Feb 2026 | Completed
Fact Intelligence | Fact normalization | Clean fact schema | 13 Feb 2026 | 13 Feb 2026 | Not Started
Fact Intelligence | Contradiction detection | Conflicts flagged | 14 Feb 2026 | 15 Feb 2026 | Not Started
Fact Intelligence | Clarification loop | Complete facts | 16 Feb 2026 | 16 Feb 2026 | Not Started
Case Law Intelligence | Ingest judgments | Judgment text extracted | 17 Feb 2026 | 17 Feb 2026 | Not Started
Case Law Intelligence | Paragraph chunking | Fine-grained chunks | 18 Feb 2026 | 18 Feb 2026 | Not Started
Case Law Intelligence | Embed & index case law | Case law searchable | 19 Feb 2026 | 20 Feb 2026 | Not Started
Case Law Intelligence | Retrieve relevant precedents | Relevant cases returned | 21 Feb 2026 | 21 Feb 2026 | Not Started
Legal Reasoning | Issue framing | Issues identified | 22 Feb 2026 | 22 Feb 2026 | Not Started
Legal Reasoning | Section applicability check | Applicability analysis | 23 Feb 2026 | 24 Feb 2026 | Not Started
Legal Reasoning | Precedent ranking | Strong vs weak cases | 25 Feb 2026 | 26 Feb 2026 | Not Started
Legal Reasoning | Counter-argument generation | Weaknesses identified | 27 Feb 2026 | 27 Feb 2026 | Not Started
Drafting | Draft templates | Templates ready | 28 Feb 2026 | 28 Feb 2026 | Not Started
Drafting | Drafting agent | Legal draft created | 01 Mar 2026 | 02 Mar 2026 | Not Started
Drafting | Court formatting rules | Court-ready draft | 03 Mar 2026 | 03 Mar 2026 | Not Started
Safety & QA | Citation verification | No fake citations | 04 Mar 2026 | 04 Mar 2026 | Not Started
Safety & QA | Hallucination blocking | Source-only output | 05 Mar 2026 | 05 Mar 2026 | Not Started
Safety & QA | Human approval gate | Manual approval enforced | 06 Mar 2026 | 07 Mar 2026 | Not Started
Final Polish | End-to-end testing | System stable | 08 Mar 2026 | 09 Mar 2026 | Not Started
Final Polish | Documentation & README | Docs complete | 10 Mar 2026 | 10 Mar 2026 | Not Started
Final Polish | Demo preparation | Portfolio-ready | 11 Mar 2026 | 11 Mar 2026 | Not Started

## Weekly Checkpoints
Week | Dates | Checkpoint Goal | Go/No-Go Criteria
Week 1 | 18–24 Jan 2026 | Local LLM + FAISS RAG works | Can answer from provided context only
Week 2 | 25–31 Jan 2026 | Bare Act Legal RAG | Correct section retrieval
Week 3 | 01–06 Feb 2026 | UI + Fact Collection | Facts captured & stored
Week 4 | 07–12 Feb 2026 | CrewAI Core Agents | Agents communicate correctly
Week 5 | 13–16 Feb 2026 | Fact Intelligence | Clean, contradiction-free facts
Week 6 | 17–21 Feb 2026 | Case Law Intelligence | Relevant precedents retrieved
Week 7 | 22–27 Feb 2026 | Legal Reasoning Depth | Issues & applicability validated
Week 8 | 28 Feb–03 Mar 2026 | Drafting | Court-ready draft generated
Week 9 | 04–07 Mar 2026 | Safety & QA | Zero hallucination
Week 10 | 08–11 Mar 2026 | Final Polish | Demo-ready system

## Buffers & Risks
Buffer Window | Purpose | When to Use
Week 2–3 | Learning curve buffer | If PDF parsing/chunking is slow
Week 4 | CrewAI complexity buffer | If agents fail to coordinate
Week 6 | Large PDFs buffer | If case law ingestion is heavy
Week 8 | Drafting buffer | If formatting takes longer
Week 10 | Final stabilization buffer | Bug fixes & polish