## Weekly Plan
Nyaymalaw 3.0 — Research Project Plan (15 hrs/week)
Hardware: RTX 4060 (8GB VRAM) ¦ Qwen2.5-7B Instruct via Ollama ¦ ~3 min/query full pipeline
# | Phase | Task | Details / Deliverable | Hours | GPU Hrs | Status | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | 1. Setup & Freeze | Freeze codebase & tag release | Git tag v3.0-eval; record exact model versions (Qwen2.5-7B quant, MiniLM-L6-v2, ms-marco-MiniLM-L-12-v2) | 3 | 0 | Pending | █
1.2 |  | Install eval dependencies | pip install matplotlib scipy; verify all eval/ scripts run; test GPU utilization | 2 | 0 | Pending | █
1.3 |  | Run 10 pilot queries | Test batch_runner with 10 sample queries to estimate per-query time and GPU usage | 4 | 1 | Pending | █
1.4 |  | Initial threshold sweep | Run threshold_sweep on pilot queries; get first score distribution plot — potential early finding | 3 | 0.5 | Pending | █ | █
1.5 |  | Calibrate time estimates | From pilot: measure actual per-query time, VRAM usage, disk I/O; adjust plan if needed | 2 | 0 | Pending |  | █
2.1 | 2. Query Set Construction | Draft 50 queries (Batch 1) | 25 legal_opinion + 15 search + 10 lookup across 8 domains; write gold bare acts + case laws for each | 10 | 0 | Pending |  | █ | █
2.2 |  | Draft 50 queries (Batch 2) | Complete to 100 queries; ensure coverage: all complexity tiers, jurisdictions, recency bands | 10 | 0 | Pending |  |  | █ | █
2.3 |  | Draft 20 additional queries | Edge cases: multi-act, constitutional, recent amendments (2023-2025), regional HC-specific | 5 | 0 | Pending |  |  |  | █
2.4 |  | Build safety test suite | 40-50 adversarial queries (extend the 20 sample ones); cover all 6 categories | 4 | 0 | Pending |  |  | █
2.5 |  | Gold annotation self-check | Cross-verify your own gold answers against SCC Online / Indian Kanoon before sharing with advocates | 6 | 0 | Pending |  |  |  | █
3.1 | 3. Advocate Annotation | Recruit 2 advocate annotators | Identify 2 practicing advocates (5+ yr experience); brief them on annotation task; share guidelines | 3 | 0 | Pending |  |  |  | █
3.2 |  | Generate annotation templates | Run annotator_agreement --generate-template; create Excel sheets for binary relevance + opinion quality | 2 | 0 | Pending |  |  |  | █ | █
3.3 |  | Advocate annotation round 1 | Advocates independently annotate 60 queries each; you coordinate and answer clarifications | 4 | 0 | Pending |  |  |  |  | █ | █
3.4 |  | Advocate annotation round 2 | Remaining 60 queries; collect all binary relevance + 5-dim Likert scores | 4 | 0 | Pending | [5 empty] | █ | █
3.5 |  | Inter-annotator agreement | Run annotator_agreement.py; compute Cohen's Kappa and Krippendorff's Alpha; resolve disagreements | 4 | 0 | Pending | [6 empty] | █
3.6 |  | Finalize gold standard | Merge annotations into single gold-standard JSON; resolve all disagreements via discussion | 3 | 0 | Pending | [6 empty] | █
4.1 | 4. Batch Evaluation | Full pipeline run (120 queries) | batch_runner --mode full_pipeline; ~6 hrs GPU time; run overnight | 4 | 6 | Pending |  |  |  |  | GPU | █
4.2 |  | FAISS-only ablation | batch_runner --mode faiss_only; no LLM calls so fast (~30 min GPU) | 2 | 0.5 | Pending | [5 empty] | █
4.3 |  | BM25-only ablation | batch_runner --mode bm25_only; CPU only, fast | 2 | 0 | Pending | [5 empty] | █
4.4 |  | Merged-no-rerank ablation | batch_runner --mode merged_no_rerank; FAISS + BM25 but skip cross-encoder | 2 | 0.5 | Pending | [5 empty] | █
4.5 |  | No-internet ablation | batch_runner --mode no_internet; full local pipeline, no fallback | 3 | 5 | Pending | [6 empty] | GPU
4.6 |  | Safety test batch | safety_runner --queries safety_queries.json; ~50 queries, 1-2 hrs GPU | 3 | 2 | Pending | [6 empty] | █ | █
4.7 |  | Citation verification | citation_verifier on all full_pipeline results; optionally --online for Indian Kanoon | 3 | 0 | Pending | [7 empty] | █
5.1 | 5. Analysis & Figures | Compute retrieval metrics | retrieval_metrics.py on all 5 ablation result files; generate comparison JSON | 3 | 0 | Pending | [7 empty] | █
5.2 |  | Full threshold sweep | threshold_sweep on complete results (120 queries); find optimal MIN_RERANK_SCORE | 3 | 1 | Pending | [7 empty] | █ | █
5.3 |  | Generate all figures | generate_figures.py: ablation bars, threshold P-R curve, score histograms, safety breakdown, radar chart | 4 | 0 | Pending | [8 empty] | █
5.4 |  | Statistical tests | 95% CIs, significance tests (paired t-test / Wilcoxon) between ablation modes | 4 | 0 | Pending | [8 empty] | █
5.5 |  | Deep-dive: failure analysis | Manually examine worst 10 queries; identify patterns (domain gaps, index quality, LLM failures) | 4 | 0 | Pending | [8 empty] | █ | █
5.6 |  | Key findings summary | Write 1-page summary of top 5 findings; identify paper's main contribution claims | 3 | 0 | Pending | [9 empty] | █
6.1 | 6. Paper Writing | System architecture section | Write Section 3 (System); architecture diagram; pipeline description; safety layer | 6 | 0 | Pending | [9 empty] | █
6.2 |  | Benchmark section | Write Section 4 (Benchmark); dataset construction, annotation process, IAA results | 5 | 0 | Pending | [9 empty] | █ | █
6.3 |  | Experiments section | Write Section 5 (Experiments); all tables and figures; ablation analysis; threshold sweep | 8 | 0 | Pending | [10 empty] | █
6.4 |  | Introduction + Related Work | Write Sections 1-2; position against Magesh et al., LRAGE, Schwarcz et al.; state contributions | 6 | 0 | Pending | [10 empty] | █ | █
6.5 |  | Discussion + Conclusion | Write Sections 6-7; limitations, lessons, future work | 4 | 0 | Pending | [11 empty] | █
6.6 |  | Abstract + references | 250-word abstract; format all references; check citation format for target venue | 3 | 0 | Pending | [11 empty] | █
6.7 |  | Internal review & revisions | Self-review; fix inconsistencies; verify all claims against data; proofread | 5 | 0 | Pending | [11 empty] | █
7.1 | 7. Submit | Prepare submission package | Camera-ready formatting per venue guidelines; supplementary materials; code/data appendix | 4 | 0 | Pending
7.2 |  | ArXiv preprint | Upload to ArXiv for priority; CS.CL or CS.AI category | 2 | 0 | Pending
7.3 |  | Submit to primary venue | AI and Law journal or IJLT; prepare cover letter | 2 | 0 | Pending
7.4 |  | Workshop paper (optional) | Shorter 8-page version for ACL NLLP workshop focusing on retrieval ablation | 6 | 0 | Pending
|  | TOTAL |  | 160 | 16.5
Legend: |  |  | Setup & Freeze |  | Query Construction |  | Advocate Annotation |  | Batch Evaluation |  | Analysis & Figures |  | Paper Writing

## Hardware & Budget
Hardware Constraints & Time Budget
Hardware Component | Spec | Constraint | Impact on Eval
GPU | NVIDIA RTX 4060 | 8 GB VRAM | Qwen2.5-7B loads ~5.5 GB; leaves ~2 GB for embeddings + cross-encoder
LLM | Qwen2.5-7B Instruct | ~300 tokens/sec | Each full-pipeline query takes ~3 min (query expansion + sufficiency + opinion generation)
Embedding Model | all-MiniLM-L6-v2 | ~80 MB VRAM | FAISS search is fast (<1 sec); loads once, stays in memory
Cross-Encoder | ms-marco-MiniLM-L-12-v2 | ~130 MB VRAM | Re-ranks 50-100 candidates per query in ~2-3 sec
FAISS Index | Local .index files | Disk I/O bound | Index size depends on corpus; v2 index loads in <2 sec
RAM | System RAM (assumed 16-32 GB) | BM25 in-memory | BM25 index fits in RAM; no constraint
Internet | DuckDuckGo API | Rate limited | Tier 2-4 search adds ~10-30 sec per gap; run fallback queries overnight
Evaluation Task | Time per Query | Total (120 queries) | Notes
Full pipeline (with LLM) | ~3 min | ~6 hrs | Run overnight; GPU at ~95% utilization
FAISS-only (no LLM) | ~5 sec | ~10 min | CPU + GPU embeddings; very fast
BM25-only (no LLM) | ~1 sec | ~2 min | Pure CPU; instant
Merged no rerank | ~5 sec | ~10 min | FAISS + BM25; no cross-encoder
No-internet (local only) | ~2.5 min | ~5 hrs | Like full but skips web search
Safety test (50 queries) | ~30 sec | ~25 min | Most blocked at content_guard; no LLM call
Citation verification | ~2 sec | ~4 min | Local index lookup; no GPU needed
Threshold sweep (offline) | ~0 sec | ~1 min | Uses pre-computed scores; pure computation
Figure generation | N/A | ~2 min | matplotlib; CPU only
Weekly Hour Budget (15 hrs/week)
Activity Type | Hours/Week | % of Time | Notes
Active coding / scripting | 4 | 26.67% | Writing eval scripts, fixing bugs, data prep
Query drafting + gold annotation | 4 | 26.67% | Biggest bottleneck — manual legal research
GPU batch runs (can overlap) | 2 | 13.33% | Runs while you do other tasks or sleep; monitor remotely
Analysis + interpretation | 2 | 13.33% | Reading results, identifying patterns, statistical tests
Writing (paper) | 2 | 13.33% | Start early with system description; iterate
Coordination (advocates) | 1 | 6.667% | Emails, calls, clarification; lighter most weeks
TOTAL | 15

## GPU Scheduling
GPU Scheduling Strategy for RTX 4060
Strategy | How To
Run batch evals overnight | Start batch_runner before bed. 120 queries x 3 min = ~6 hrs. Set up logging so you can check results in the morning.
Ablation modes don't need LLM | faiss_only, bm25_only, merged_no_rerank are fast (<15 min total). Run these during work hours — they barely use GPU.
Safety tests are mostly CPU | Most adversarial queries get blocked by content_guard.py regex (no LLM call). Only ~10-15% reach the LLM. Total: ~25 min.
Threshold sweep is offline | Uses pre-computed rerank scores from batch results. Zero GPU. Run any time in under 1 minute.
Avoid running Ollama + training simultaneously | Qwen2.5-7B uses ~5.5 GB of 8 GB VRAM. Don't run other GPU workloads during batch eval runs.
Use screen/tmux for long runs | Start batch jobs in tmux so they survive terminal disconnects: tmux new -s eval && python -m eval.batch_runner ...
Monitor GPU with nvidia-smi | Run 'watch -n 1 nvidia-smi' in another terminal to monitor VRAM and utilization during runs.
Internet fallback is the slowest part | DuckDuckGo search + PDF download can add 30-60 sec/query. no_internet mode skips this — run it first for quick results.
Incremental saves | batch_runner saves results after each query. If interrupted, you have partial results. Resume by filtering already-done queries.
Parallel annotation while GPU runs | Draft queries and gold annotations while batch jobs run. GPU time is 'free' time for manual work.

## Risks & Mitigations
Risk Register
Risk | Likelihood | Impact | Mitigation | Week
FAISS index has too much junk data | High | High | Already partially fixed (quality filters + 0.55 threshold). Threshold sweep will quantify. If >60% junk, rebuild index from curated PDFs only. | 1-2
Advocates unavailable or slow | Medium | High | Start recruiting in Week 4. Have 3 candidates (need only 2). Offer co-authorship for substantial contribution. Budget 4 weeks for annotation. | 4-7
LLM hallucinates case names | High | Medium | citation_verifier.py catches this. Report hallucination rate as a key metric. Consider adding post-generation citation check in production. | 8
Internet fallback returns 0 results | Medium | Medium | DuckDuckGo site: searches can fail. Mitigation: test connectivity before batch runs; use no_internet as baseline anyway. | 5-8
Qwen2.5-7B too weak for legal reasoning | Medium | High | This IS a finding, not a failure. Report it honestly. Compare with GPT-4/Claude if budget allows for a small subset (10 queries). | 8-10
Not enough queries for statistical significance | Low | High | 100-120 queries with 2+ annotators gives reasonable power. For key metrics, compute 95% CIs. If CIs too wide, add 20-30 more queries. | 7-8
Reviewer asks for comparison with cloud LLM | High | Medium | Pre-empt: run 10-20 queries through GPT-4 API as a reference point. Budget ~$5-10 for API calls. Frame as 'local vs. cloud' analysis. | 9-10
Paper rejected from primary venue | Medium | Low | Have backup venues (IJLT, JURIX, ACL NLLP workshop). Different venues have different focus — retarget if needed. | 14-15